## Sheet1
| ESTMATED | 1st Sprint Product Backlog | dependency
1. get_articles (group member) | 12 | 12
2. comment_article (group member) | 4 | 4
3. create_article (group member) | 4 | 4
4. delete_article (article owner/group owner) | 2 | 2
5. report_article (group member) | 5 | 4
1. upvote_article | 4 | 4
2. downvote_article | 4 | 4
1. create_group (logged in user) | 4 | 0
2. delete_groups (group owner) | 4 | 5
3. add_member (group owner) | 3 | 1 | invite
4. accept_invitation (prospective group member) | 2 | 2
5. request_membership (prospective group member) | 2 | 4
6. approve_membership (group owner) | 2 | 4
7. block_member (group owner) | 3 | 0
8. invite_member (group member) | 5 | 5
9. update_group (group owner) | 3 | 3
10. report_member/report_article (group member) | 3 | 3
1. get_top_members (group member) | 2 | 0
2. get_group_description (logged in user) | 1 | 2 | integration
3. search_groups (logged in user) | 2 | 0
4. view_all_users (group memnber) | 2 | 0
1. login | 2.5 | 0
2. register | 2 | 0
3. change_password (logged in user) | 2 | 0
4. forgot_password | 2 | 0
5. update_profile (logged in user) | 2.5 | 0
6. change_profile_pic (logged in user) | 2 | 2
7. logout (logged in user) | 0 | 0
8. search_users (logged in user) | 1 | 1
9. search_all (logged in user) | 2 | 4 | articles
10. view_profile (logged in user) | 1 | 1
Total Effort | 90 | 71